## Procurement Plan
Guidelines for project implementation by grant beneficiaries – Tool 6 - Template for a Procurement Plan
Contract No.:
Contract Title:
Grant Beneficiary:
Item | Lot No (if applicable) | Project Budget |  |  | Budget line (Annex III) | Title of the Contract | Type of procurement | Procurement procedure | Tender launch date (date od sending invitations/date of publication) | Tender Evaluation Date | Contract signature date by second party | Completion of the contract (services)/ acceptance of goods (supply)
|  | Unit | Unit price | Total (Euro)
Procurement 1 | Lot 1 | 600 | 3 | 1800 |  | Publications - survey results and study | Service | Single Tender
| Lot 2 | 600 | 3 | 1800
Procurement 2 |  | 500 | 10 | 5000 |  | Catering | Service | Single Tender
Procurement 3 |  | 1 | 25000 | 25000 |  | Expert on advocacy | Service | Simplified procedure
NOTES:
1. Follow the procurement principles outlined in Annex 4 of the Grant Contract .
2. Generally, market research should be undertaken for all procurement processes to ensure value for money.
3. When undertaking market research for supplies, do not disclose the budget amount. Do not copy verbatim technical specifications from one supplier into a tender dossier. Signing a supply contract for the exact budget amount (for example, a budget amount of €2,357 for a piece(s) of equipment and signing a contract for €2,357) will likely be subject to review and may result in ineligible expenditure.
4. With the exception of very small amounts, for value for money and fair competition purposes, it's strongly advised to invite at least three service providers/suppliers to submit an offer. (Receipt of 1-2 offers is fine to finalise the procurement process).
5. For supplies, choose the lowest priced administrative, technical and financially compliant offer.
6. For services, choose the most technically and economically advantageous (evaluation based on a combination of technical criteria and price) compliant offer.
7. In a budget with a large number of communication and visibility items, group items into one tender to the extent possible and invite at least three providers to submit an offer. Also, group other items that can be provided by one supplier, such as organisation of event.