Guidelines for project implementation by grant beneficiaries

This Guidelines for project implementation by grant beneficiaries are designed to support awarded Grant Beneficiaries when implementing grant contracts in the context of the 3rd CfP within the IPA Cross-Border Cooperation Programme Montenegro – Albania 2014-2020, reference number EuropeAid/171769/ID/ACT/MULTI.

This document is the sole responsibility of Contracting Authority and do not necessarily reflect the views of the European Union.

Table of Contents

Standard Grant Contract			8

Grant contract modifications		14

Financial Management			20

Secondary Procurement			32

Monitoring, Evaluation, Compliance	36

Reporting					42

Visibility					47

List of Tools

- Tool 1: Contract Modification Templates

- Tool 2: Checklist for Accounting System

- Tool 3: Documentation checklist

- Tool 4: Timesheet template

- Tool 5: Set of secondary procurement packages

- Tool 6: Procurement Plan template

- Tool 7: Templates for Interim and Final reports

- Tool 8: Financial reporting details

- Tool 9: Reporting checklist

- Tool 10: Template for Communication and Visibility Plan

- Tool-11: VAT Exemption request

According to the Article 2 of the Special Conditions, the contract enters into force on the date when the second of the two parties signs. Implementation of the action starts on the day following that on which the second of the two parties signs or on a later date, defined by the beneficiary. For any grant to be successfully implemented, there needs to be some good work done, some administration taken care of and some rules respected. The following Guidelines provide some useful guidance for you as Grant Beneficiary– give some instruction and provide some tools; as follows:

- Chapter 1 gives you an overview of the grant contract requirements. Look there for explanations related to all grant contract annexes and what they relate to. It also gives you information on the way’s contracts can be modified. This chapter is accompanied by the tool you can use when modifying contracts. (Tool 1 – Word template for the request for amendment; Tool 1 – Excel template for budget amendment). You will find explanations in this Chapter on the steps you should take when requesting modifications to the contract, and it is recommended that you use the tools attached when requesting such modifications.

- Chapter 2 gives you the information on financial/administrative management, including planning, payment claims, accounting and documentation keeping. This chapter is accompanied by two tools – checklists, for accounting system and for documentation. And, also there is a convenient template for timesheets, which you can use for staff and experts providing services within your grant project. Tools for accounting system and documentation are for your own convenience, you do not need to submit them to the Contracting Authority, but you are welcomed to use them within internal quality control under your grant actions.

- Chapter 3 gives you information in relation to secondary procurement. It refers to all procurement of services, supplies and works that you will be conducting within your grant actions. In relation to these, there are two tools – ‘packages’ for single and simplified procedures templates you may decide to use while procuring under your grant project. CFCU, your Contracting Authority clearly recommends these and you are advised to consider using them. This Chapter directs you to PRAG – Practical Guide for EU External Actions. Note that projects financed under this Call for Proposals (CfP) will follow the PRAG version 2020.

- Chapter 4 gives you information in relation to monitoring. Internal monitoring is the monitoring that you are conducting yourself, and external monitoring is conducted by JTS, CBC Bodies, Control Body and CFCU.

- Chapter 5 gives you information in relation to reporting. You are obliged to send interim and final reports, as defined in your contracts. As part of your contract you are already provided with templates for such reporting. These include narrative interim and final reports and financial reports and you may find them attached to this Chapter. Note that reporting is of utmost importance in EU grants – it is linked with payments of further pre-financing, among other matters and The reporting period is every 12 months covered with the interim reports and final report at  the completion of the project, as general rule set within the General and Special Conditions within this CfP.

- Chapter 6 gives you information on the visibility requirements. It directs you to the EU visibility requirements titled 'Communication and Raising EU Visibility', which came into force on July 2022, and apply to all EU funded contracts signed from that date, including those under the 3rd CfP  within the IPA CBC Programme Montenegro – Albania 2014-2020, reference number EuropeAid/171769/ID/ACT/MULTI. There is a tool also here – template for Communication and Visibility activities under your grant actions, which you are strongly advised to use.

In the preparation of these Guidelines, the following sources were used:

- DEVCO Companion Ver.14.0 (June 2022)

- PRAG Ver.2020

- Financial Management Toolkit for recipients of EU funds for external actions (2014, EC).

Glossary of main terms:

ACTION (also: project): Global term for beneficiary activities funded by the EU (via grants, procurement, prizes or financial instruments). Often used as a synonym for beneficiaries’ “projects”. In this context ‘grant action’ – grant for a project or specific activity.

AFFILIATED ENTITY: Organization that has a link with a grant beneficiary (in particular a capital or legal link), which is NOT limited to the action or established for the sole purpose of implementing it. Defined as such in the proposal.

ASSOCIATES: Other organisations or individuals (other than Lead applicant, co-applicant and affiliated entities) involved in the action.  Associates play a real role in the action but may not receive funding from the grant, with the exception of per diem or travel costs. Associates are mentioned in Part B, Section 6 — ‘Associates participating in the action’ — of the grant application form.

CBC BODIES: Part of the operating structures of the IPA Cross-border Cooperation Programme Montenegro-Albania 2014-2020 (IPA CBCP MNE-ALB 2014-2020). The Montenegrin and Albanian CBC Bodies are jointly ensuring all tasks related to the implementation of the Programme including management of technical assistance under the Programme. They are also responsible for the monitoring of the Programme. The Cross-border Cooperation bodies within the Programme are Government of Montenegro – Ministry of European Affairs, Directorate for European Funds and the State Agency of Strategic Programming and Aid Coordination of the Republic of Albania, Directorate for Administration of EU Financial Assistance.

CONTROL BODY: The Control Body is an integral part of the management and control system and his duties are discharged by the Ministry of Finance and Economy of the Republic of Albania.

CONTRACTORS: Contractors are subject to the procurement rules set out in Annex IV to the standard grant contract. Associates or affiliated entity(ies) cannot be also contractors in the project.

CONTRACTING AUTHORITY: Grant contracts are managed by the Contracting Authority (CA). In the context of the 3rd CfP within the IPA CBCP MNE-ALB 2014-2020 reference number EuropeAid/171769/ID/ACT/MULTI, the role of the Contracting Authority (CA) is performed by the Directorate for Finance and Contracting of the EU Assistance Funds (CFCU) within the Ministry of Finance of Montenegro.

COORDINATOR/EX LEAD APPLICANT: When awarded the grant contract, the lead applicant becomes the beneficiary identified as the coordinator in Annex G (special conditions).Lead applicant as coordinator is the main interlocutor of the contracting authority. It represents and acts on behalf of any other co-beneficiary and coordinates the design and implementation of the action. The Coordinator is the lead grant beneficiary in a group of Grant Beneficiaries and is the main contact point for the Contracting Authority. The Coordinator provides narrative and financial reports, requests necessary payments, and is ultimately responsible for project finances and records. Detailed description of Coordinator, its role and responsibilities are explained under Article 1.6 of GC.

GRANT BENEFICIARY: Organization that receives EU funding in the form of a grant. Term collectively refers to all awarded co-applicants under the action. Namely, grant beneficiaries are Lead Applicant, Co-applicant/s and Affiliated Entities (if any). Detailed description of GBs, its role and responsibilities are explained under Article 1.5 of General Conditions (GC).

IPA is Instrument for pre-accession assistance is the means by which the EU supports reforms in the 'enlargement countries' with financial and technical help.

JTS: The Joint Technical Secretariat of the Cross-border Cooperation Programmes Montenegro – Albania and Montenegro – Kosovo 2014-2020 is responsible for the day-to-day management of the programme (providing technical assistance) including support and advice to all potential applicants and grant beneficiaries in the Programme area. The JTS has an antenna located in Shkodra (Albania). The JTS, including Antenna office, is the main contact point for the applicants and grant beneficiaries of the IPA CBCP MNE-ALB 2014-2020. In the JTS a dedicated Project Officer will be responsible to support the grant beneficiaries and monitor the action.

PRAG is practical guide to contract procedures for EU external actions. PRAG provides practical assistance in terms of rules and procedures to Contracting Authorities and tenderers, candidates, applicants and contractors in preparing and implementing procurement and grant contracts.

REPORTING PERIOD: Longer projects are divided into reporting periods, to allow for regular reporting and interim payments.

Abbreviations:

| Action | Grant – financed project |
| --- | --- |
| ALB | Albania |
| CA | Contracting Authority |
| CFCU | Directorate for Finance and Contracting of the EU Assistance Funds (CFCU) within the Ministry of Finance of Montenegro. |
| CfP | Call for Proposals |
| CB | Control Body |
| CBCP | Cross Border Cooperation Programme |
| EUD MNE | EU Delegation to Montenegro |
| GB | Grant Beneficiaries |
| GC | General Conditions (Annex II to the Grant Contract) |
| IPA | Instrument for pre-accession assistance |
| JMC | Joint Monitoring Committee |
| JTS | Joint Technical Secretariat |
| LFA/LFM | Logical Framework Approach/Logical Framework Matrix |
| M&E | Monitoring and Evaluation |
| MNE | Montenegro |
| OS | Operating Structures |
| PRAG | Practical guide to contract procedures for EU external actions |
| RMB | Results Based Management |
| SC | Special Conditions (first part of the Grant Contract) |
| TA | Technical Assistance |
| TD | Tender dossier |
| ToR | Terms of Reference |
| VAT | Value Added Tax |

Standard Grant Contract

C H AP T E R

1

Grant contract is consisted of several annexes. The General Conditions (GC) contain the basic essential articles governing the implementation phase for grants contracts. They are complemented and may be subject to modification by the Special Conditions (SC) that are part of the grant contract and that also include any necessary supplementing clauses or derogations to the general conditions, taking into account the specific circumstances of the action or work program to which the contract relates. These special and GC, together with the other annexes to the contract, are the legally binding documents that govern the parties' rights and obligations under the contract.

grant contract

- Special Conditions

- Description of the Action (Annex I)

- GC plus Annexes (Annexes II to IX)

The following documents are annexed to the special conditions and form an integral part of the contract:

- Annex I: Description of the action (including the logical framework of the project and the concept note)

- Annex II: General conditions applicable to European Union-financed grant contracts for external actions

- Annex III:  Budget for the action (worksheets 1, 2 and 3)

- Annex IV: Procurement rules for beneficiaries

- Annex V: Standard request for payment and financial identification form

- Annex VI: Model narrative and financial report and the list of programme indicators

- Annex VII: Terms of reference for an expenditure verification of a Union financed grant contract for external actions and model report of factual findings

- Annex IX: Standard template for transfer of asset ownership

The SC prevails over the GC which takes precedence over all the other annexes.

The table below provides more information on the specific parts of the standard grant contracts.

| Document | Description | Practical aspects |
| --- | --- | --- |
| Special conditions | Determines the basic rules of the contract including implementation period, instalments and reporting requirements. The document, supplemented with annexes, represents the legal basis for contractual relation between the grant beneficiary and the Contracting Authority (CFCU) | Defines the purpose of the action, maximum grant available, implementation period of the action, financing the action, co-financing requirements, reporting and payment arrangements, contact addresses and annexes. |
| Description of the action | Annex I to the grant contract provides detailed description of the project as proposed by the grant beneficiary in the application phase. | The anticipated activities, results and indicators to be closely followed. Any discrepancy to be reported to the CA. Note the following: Changes in Description of the Action and the Logical Framework that affect the expected results (impact, outcomes, outputs) shall be agreed in writing with the Contracting Authority before the modification takes place. Approved changes must be explained in the next report. |
| General conditions | Annex II sets up general and administrative provisions of project implementation. | Document covering all the implementing rules and aspects. To be consulted in each formal step/issue in the implementation phase. |
| Budget of the action | Annex III of the contract provides detailed financial structure of the project as proposed by the grant beneficiary in the application phase and agreed during the budget clarification process. | The original budget cannot be exceeded in the implementation. Amendments of the budget to be implemented in line with the procedure. Note the following: Where the amendment to the budget does not affect the expected results of the action (i.e. impact, outcomes, outputs), and the financial impact is limited to a transfer between items within the same main budget heading including cancellation or introduction of an item, or a transfer between main budget headings involving a variation of 25% or less of the amount originally entered (or as modified by addendum) in relation to each concerned main heading for eligible costs, the Coordinator may amend the budget and must inform the Contracting Authority accordingly through the notification letter, in writing and at the latest in the next report. Changes above 25% and those requiring change of details in SC, such as duration of the project, for example, will require an addendum. The grant beneficiary shall send the Request for an Addendum, at least 30 days before the addendum should enter into force, presenting the reasons for the addendum to the Contracting Authority. If the Contracting Authority finds these reasons as justified, the procedure for ex-ante approval of such addendum, by the EU Delegation to Montenegro will also be conducted. So, pay attention to the fact that any addendum approval is a very lengthy process! |
| Contract award procedures | Annex IV to the grant contract sets down the rules for procurement by the Grant Beneficiaries. | Used when purchasing services, supply or works (normally the main budget headings 3, 4, 5 and 6). Grant beneficiaries should ensure that the rules are fully respected. Note the following: The beneficiary may decide to apply the procurement procedures set forth in the practical guide (PRAG). If these procedures are correctly followed the principles defined in Annex IV will be deemed to be complied with. These principles are: - Best Value for Money - Avoidance of conflict of interest - Being able to justify the choice of tenderer - Using objective criteria in evaluation - Record keeping - Respecting EU restrictive measures |
| Request for payment | Annex V standard template needed when requesting funds from the CFCU. | This template shall be completed by the grant beneficiary when the interim/final payment is requested, in line with the provisions of the contract. |
| Model of narrative and financial report | Annex VI Standard template used for reporting on activities and finances of the EU funded grant project. | Templates to be used in the exact form to report proceedings on the project, including financing aspects. |
| Terms of reference for an expenditure verification of an EU financed grant contract | Annex VII. Standard template for expenditure verification. | Anticipates engagement of an independent auditor. The auditors’ report needs to follow the templates provided in Annex VII. Note the following: Expenditure verification is mandatory within this CfPs as the minimum amount of the EU-funded grant was higher than 100 000 Eur. |
| Transfer of Ownership of Assets | Annex IX template to be used in case of transfer of ownership of an equipment/supply to the local partners and/or final beneficiaries. | Coordinator to ensure transfer of ownership before conclusion of the project. Certificate to be provided with the final report. |

Each of these documents, and GC imply certain principles and provisions. Below are some important general provisions and principles of grant contracts:

GRANT BENEFICIARIES

- The grant beneficiary(ies) and the Contracting Authority are the only parties to this contract. It means that organizations perhaps affiliated with the grant beneficiary(ies) but not identified as affiliated entities to the grant contract, potential service providers and contractors or those commissioned during the implementation – are not a party to the grant contract.

- The term 'beneficiaries' refers collectively to all Grant Beneficiaries of the action. These include the Coordinator (the Lead Beneficiary) and partners (co-beneficiaries).

- By default, the Coordinator signs on behalf of all (other) Grant Beneficiaries.

- All Grant Beneficiaries are jointly responsible to ensure that the action is carried out in accordance with the description of the action in Annex I and the terms and conditions of the contract (operational responsibility). However, vis-à-vis the Contracting Authority, the financial responsibility for the implementation of the entire action including the parts implemented by co-beneficiaries and affiliated entities rests with the Coordinator. This means that the Contracting Authority will, where necessary, recover funds only from the Coordinator.

THE ROLE OF THE COORDINATOR

The grant action is led by the Lead Beneficiary listed in the contract as the Coordinator. Such organization has a special role within a contract, as defined below:

- The Coordinator is the sole interlocutor of the Contracting Authority and is responsible for collecting all the necessary information for drawing up consolidated reports. The Coordinator is therefore responsible for obtaining, verifying and consolidating this information before passing it on to the Contracting Authority. All Grant Beneficiaries (GBs) agree that any information given, as well as any request made by the Coordinator to the Contracting Authority, must be deemed in agreement with all Grant Beneficiaries.

## Some tips on partnership/stakeholder management

Prepare a partnership agreement! It is of the great importance to define responsibilities between all partners throughout the implementation period



- Ensure that you list all tasks and responsibilities among partners;

- Communication is the key for good partnership

- Good internal communication is a prerequisite for efficient external communication;

- Regular meetings are important. Make minutes of those meetings and use them as working documents!

- Agree on when and how and on what are you and your partners communicating;

- Make a format for internal reports;

- Agree on tools that will be used: e-mail, phone meetings, real meetings;

- Plan a project kick off meeting with all partners;

- Agree or confirm there on exact roles of each partner and on reporting obligations (including reporting deadline for partners to Coordinator).

ROLE OF THE CONTRACTING AUTHORITY, CONTROL BODY AND CROSS-BORDER COOPERATION BODIES (CBC BODIES)

Contracting Authority coordinates, manages and oversees the implementation and monitoring of the grant schemes, approves grant contracts and any amendments of the contracts (notifications and addenda); approves reports, makes all final decisions related to eligibility of expenditure and contractual compliance and reimburses eligible project costs to Grant Beneficiaries. The contracting Authority of the IPA CBCP MNE-AL 2014-2020 under which the contracts have been signed is Directorate for Finance and Contracting of the EU Assistance Funds (CFCU) within the Ministry of Finance.

Cross-Border Cooperation Bodies (CBC Bodies) are part of the Operating Structures of the IPA CBCP MNE-ALB 2014-2020. The Montenegrin and Albanian CBC Bodies are jointly ensuring all tasks related to the implementation of the Programme including management of technical assistance under the Programme. They are also responsible for the monitoring of the Programme. The CBC Bodies within the Programme are Government of Montenegro – Ministry of European Affairs, Directorate for European Funds and the State Agency of Strategic Programming and Aid Coordination of the Republic of Albania, Directorate for Administration of EU Financial Assistance.

CONTROL BODY: The Control Body is an integral part of the management and control system and his duties are discharged by the Ministry of Finance and Economy of the Republic of Albania. Namely, the Control Body preforms the verification of expenditures incurred by Albanian partners in the project.

LIABILITY

- The fact that the EU, via the CFCU, in grant schemes financed under IPA CBCP MNE-ALB 2014-2020, is financially supporting the grant action does not transfer any responsibility for circumstances resulting from the implementation of the action to the EU or the Contracting Authority. This responsibility rests entirely on the Grant Beneficiaries.

CONFLICT OF INTEREST AND CODE OF CONDUCT

In line with Article 4 of the GC, ‘‘The beneficiary(ies) shall take all necessary measures to prevent or end any situation that could compromise the impartial and objective performance of this contract. Such conflict of interests may arise in particular as a result of economic interest, political or national affinity, family or emotional ties, or any other relevant connection or shared interest.’’ Inter alia, this also means:

- During the performance of the contract, the grant beneficiary(ies) must immediately inform the Contracting Authority of any arising conflict of interests and measures should be adopted to address situations that may objectively be perceived as a conflict of interest. These measures may include the termination of the contract, as need be. The Contracting Authority reserves the right to verify that the measures taken are appropriate and may require additional measures to be taken if necessary.

- Grant beneficiary(ies) must immediately report to the Contracting Authority any allegation of misconduct involving sexual exploitation, abuse and harassment. As a minimum this notification should include the following information about the report/allegation e.g. misconduct category, type and short description. It is for the Contracting Authority to assess the gravity of the misconduct, taking into account possible remedial measures taken.

- Grant beneficiaries must respect applicable rules, procedures and policies – including the respect for fundamental human rights, social justice and human dignity, respect for the equal rights of men and women, prohibition of forced labour and child labour, preservation of the environment, respect of all laws of proper jurisdiction including the principles of transparency, non-discrimination, anti-corruption and ethics, avoidance of conflicts of interest, fraud and corruption.

- The execution of the grant contract shall not give rise to unusual commercial expenses. This includes commissions not paid in return for any actual service. The Contracting Authority could declare ineligible any abnormal high price charged to the action while buying goods or contracting services. In this situation, the overprice paid could be considered ineligible if the beneficiaries do not provide a justified reason.

- Violating intellectual property rights, attempting to obtain confidential information that may confer upon it undue advantages in the award procedure, fraudulently or negligently misrepresenting information required for the verification, are only some of types of grave professional misconduct, which may lead to suspension or termination of the grant contract.

Note

OWNERSHIP OF RESULTS

Start of Implementation is specified in art. 2.2 of Special Conditions:

Costs are eligible only after-Action start date!

Implementation ends following certain number of months after the start of the action, as defined in art. 2.3 of Special conditions.

Execution of the contract ends when final payment is paid by CA or in any case at the latest 18 months after the end of implementation period (unless postponed in accordance with art. 12.5 of the General Conditions.

Costs are eligible only during implementation period, except costs relating to final reports, including expenditure verification, audit and final evaluation of the Action, which may be incurred after the

implementation period of the Action.

- By default, the Grant Beneficiaries own any intellectual or industrial right developed in the course of the action such as patents, trademarks, copyright etc. However, the Contracting Authority must be granted a non-exclusive right to use, free of charge, all of the results, reports and other documents produced in the course of the action.

- The grant beneficiary(ies) shall ensure that it has all rights to use any pre-existing intellectual property rights necessary to implement this contract.

- In case natural, recognizable persons are depicted in a photograph or film, the Coordinator shall, in the final report to the Contracting Authority, submit a statement of these persons giving their permissions for the described use of their images.

- The principle to keep in mind is to transfer the items procured with the budget of the grant action (and therefore also with co-financing funds) to the entities that are in the best position to use them efficiently for the sustainability of the action once it ends. Where the description of the action already foresees that items will be transferred to other entities than final beneficiaries or may be kept by the beneficiaries/affiliated entities the Contracting Authority has approved this approach by signing the contract and a separate written request is not necessary.

BUDGET OF THE ACTION

  - Budget includes all eligible project costs, not just the EU contribution

  - There is a double ceiling for EU financing (art. 3(2)SC) – maximum amount and % of total eligible costs.

| How to understand this double ceiling – where there is maximum nominal amount of grant specified and then there is also % of total costs specified. Take for example the following case: Organization ‘Blue lights’ has applied for and have been awarded a grant, for a total budget of 247.058,82 EUR, where a grant is 85% of this budget. However, their actual costs, at the end of the action are higher, 270,000 EUR as they had failed to conduct a good market research and had to pay more for certain equipment. Regardless, their actual grant amount will remain 210,000 EUR – as specified nominally in their contract. Take another case as an example, organization ‘Yellow beams’ has applied for and been awarded a grant, for a total 210,000 EUR, where a grant is 85% of this budget. However, they were simple not able to procure that piece of equipment intended and their actual costs at the end of the action for the overall budget spent (co-financing included) are 210,000 EUR. Does this mean that they shall receive 210,000 EUR? No! Their actual grant amount will be 178.500 EUR – 85% of the total actual costs under the project. Project total budget 247.058,82 € | Project actual cost (Example 1) 270.000 € | Project actual cost (Example 2) 210.000 € |
| --- | --- | --- |
| Grant amount (e.g.85%) 210.000 € | Actual grant amount 210.000 € | Actual grant amount 178.500 € |

# Grant contract modifications

While managing your grant actions, it is important to know how to proceed in cases of changes that may be required.

Modifications need to be set out in writing according to the procedures provided for in Article 9.(3) and 9(4) of the GC. Oral arrangements or an exchange of emails shall never legally bind the parties in this regard. Also note that no amendment to the Grant Contract (either minor changes or by addendum) may call into question the initial award of the grant or the equal treatment of applicants.

The maximum EU contribution and percentage of eligible or accepted costs financed by the Contracting Authority may never be increased.

Article 9(4) – GC state that ’Where the amendment to the budget does not affect the expected results of the action (i.e. impact, outcomes, outputs), and the financial impact is limited to a transfer between items within the same main budget heading including cancellation or introduction of an item, or a transfer between main budget headings involving a variation of 25% or less of the amount originally entered (or as modified by addendum) in relation to each concerned main heading for eligible costs, the Coordinator may amend the budget and must inform the Contracting Authority accordingly, in writing and at the latest in the next report. This method may not be used to amend the headings for indirect costs, for the contingency reserve, for in-kind contributions or the amounts or rates of simplified cost options defined in the contract. Changes in Description of the Action and the Logical Framework that affect the expected results (impact, outcomes, outputs) shall be agreed in writing with the Contracting Authority before the modification takes place. Approved changes must be explained in the next report.’

ADDENDUM REQUEST

Based on the text of the Article 9(4) above, one can conclude that, amendment by addendum is required in those cases where:

- The modification of the Budget or Description of the Action affects results of the action and/or

- The financial impact includes:

  - A transfer between main budget headings involving a variation of more than 25% of the amount originally entered in relation to each concerned main heading for eligible costs, or

  - An amendment of the headings for indirect costs, for the contingency reserve, for in-kind contributions (including volunteers work) or the amounts or rates of simplified cost options, and;

In addition, any change of details depicted in SC of the grant action such as:

- legal status and the name of the signatories to the contract (Grant Beneficiaries); including inclusion or exclusion of Grant Beneficiaries from the grant contract;

- duration of the action and

- changes in affiliated entities.

The following should be considered in cases where addendums are concerned:

- Contracts cannot be amended after the end of the execution period. Note that the execution period of the contract is longer than the implementation period.

- The beneficiary bears the financial risk of any costs incurred before the addendum has been issued, because the Contracting Authority has the right to refuse to sign the addendum. Only once the addendum enters into force may the beneficiary claim payment for the costs.

- An amendment request must be duly substantiated and, in particular, must include all information necessary for the Contracting Authority to take an informed decision on this matter including (but not limited to): the reasons behind the amendment, and the impact of the amendment on the implementation of the action (i.e. and most notably on the activities and budget of the action).

- An amendment must be requested at least 30 days before it occurs. However, whenever possible, as the Contracting Authority may take longer to assess the amendment, it is recommended to send a request for amendment as early as possible.

- The amendment to the contract must be signed by the same parties who signed the initial contract, i.e. the Coordinator and the Contracting Authority.

- A request extending the implementation period of the action may not entail an increase of the EU contribution (no cost extension) and always requires an addendum in accordance with Article 9(1). and a proper justification, which must not be limited to using the unspent budget balance.

MINOR CHANGES

Minor project change is a change that cannot significantly jeopardize project implementation. Minor changes in the contract may be implemented without receiving a prior agreement of the CFCU, but should be notified at the latest in the next report (progress or final report). The Coordinator will ensure that at least the JTS is notified and consulted in advance.

In case of minor Contract changes, the Grant Beneficiary may apply the amendment without the prior consent of the CFCU. The Grant Beneficiary are invited to send a Notification Letter (in the format shown in Tool-1-Template-for-Notification-Letter), with a copy to the JTS and the CB, no later than 10 days after making the modification. The CFCU will review the notification and may oppose the GB’s modification and prepare a written notification on approval/rejection of the modification to the GB. CFCU will inform accordingly the Control Body in Albania about acceptance or rejection of the requests for the Grant Beneficiaries from Albania.

Minor modifications that require only written notification to the CFCU, JTS and CB by GB and no formal Addendum may include:

- Minor changes in activities with no budgetary implications;

- Budget modifications that do not affect the basic purpose of the project; and the financial impact is limited to a transfer within the same main budget heading including cancellation or introduction of an item, or a transfer between budget headings involving a variation of 25% or less of the amount originally entered under each relevant heading for eligible costs (not applicable to the heading for Administrative costs and Contingency reserve);

- Change of address or phone number;

- Change of bank account;

- Change of auditor;

- Change of the members of the project team;

- Increase or decrease in numbers of equipment or unit prices without changes of the budget amount allocated for that budget item.

Example: Minor change From the date when the project is submitted to the date of the Contract Award, more than 10 months passed. The project team is not the same and some planned project activities are partially implemented by other project such as youth campaign. This requires Grant Beneficiary to make change in the project team and in timeline of activities.

In case of minor budget change you may attach to the Notification letter (in addition to the summarized table which is part of the Notification letter) the modified Budget of the Action. The format that you may use is shown in the Tool-1-Template-for-budget-modification.

MAJOR CHANGES

Major modifications in the contract require a formal Addendum to the contract to be signed before their implementation. In case of major modifications of the Contract, an Addendum should be prepared before making the change.

In case of major changes requiring Contract Addendum, the Coordinator is advised to consult the responsible Contract Manager in the CFCU and the responsible Project Officer in the JTS, prior to the request. The Coordinator shall submit a request for an Addendum, using standard template given in the Tool-1-Template-for-Addendum-Request, with a copy to the JTS and CB, at least 30 days before the date on which the amendment should enter into force, unless there are special circumstances duly substantiated by the GB and accepted by the CFCU. The request for Addendum should include a detailed justification.

The responsible Contract Manager examines the request for Addendum and rejects requests which have little or no substantiation. The Contract Manager will recommend to the Head of CFCU to approve requests for Addendum that are properly substantiated and do not question the grant award decision and are not contrary to the principle of equal treatment of Applicants. CFCU will inform accordingly the Control Body in Albania about acceptance or rejection of the requests for the Grant Beneficiaries from Albania.

Major modifications that require a formal Addendum are as follows:

- Extension or early closing of the Grant Contract period

- Transfers amongst budget headings which involve a variation between budget headings of more than 25% of the amount originally entered under each relevant heading for eligible costs

- Addition or cancellation of a new budget item in the Budget (only if the change implies a variation of more than 25% of the amount originally entered under each relevant heading for eligible costs)

- Change of project partners (addition or replacement)

- Changes in your organisation’s name or legal status

Article 9 of the GC describes the rules and procedures to be followed for Amendments of the Contract.

The templates that you may use for the implementation of project amendments are available in the Tool 1 – Contract Modification.

How to proceed with these ‘changes requests’?

##### Steps to follow

For requesting addendum (changes requiring an addendum to the contract):

- Consult with JTS Project Officer assigned for your project before doing any steps;

- Prepare the draft request for addendum;

- If the requested modification affects the project budget, prepare the Addendum table with clearly marked affected budget lines and budget headings and indicate changes, if required, in the Justification sheet of the budget (check Tool 1 – Budget modifications)

- Review Description of the Action including the action plan for implementation, Log-frame and Budget and observe if any changes are needed and if so, mark them and mention in the request;

- Consult the draft-Request for Addendum with JTS and seek their  advice and assistance for further step (note that the recommendations provided by JTS have advisory character and do not prejudice the opinion or measures taken by the Contracting Authority);

- At least 30 days before the date on which the amendment should enter into force, submit the Request for Contract modification to the Contracting Authority (CFCU);

- Sign an Addendum to the contract (in case the CFCU approves the Request);

- Apply the modification(s), as agreed with the Addendum.

For introducing minor changes (changes not requiring an addendum to the contract, in line with Article 9(4) of GC

- Consult with JTS Project Officer assigned for your project before doing any steps;

- Prepare the Notification on the changes;

If the requested modification affects the project budget, prepare the Budget modification table with clearly marked affected budget lines and budget headings and indicate changes, if required, in the Justification sheet of the budget; (check Tool 1 – Budget modifications)

##### Attached to this Guidelines is Tool 1 – Contract modifications which you can use when introducing changes mentioned in here.

- Review Description of the Action, Log-frame and Budget and observe if any changes are needed and if so, mark them and mention in the request;

- Consult the draft-Notification on minor changes with JTS and seek their advice and assistance for further step (note that the recommendations provided by JTS have advisory character and do not prejudice the opinion or measures taken by the Contracting Authority);

- Preferably 10 days before the date of applying the modification, inform in writing the Contracting Authority about the change(s) that should be introduced.

For notifying on other changes (changes of addresses, bank accounts and auditor, for example):

- Consult with JTS Project Officer assigned for your project before doing any steps;

- Prepare the  letter notifying on the changes

- Submit the notification to the Contracting Authority

Annexed to this Guidelines is a template you can use when requesting addendum and when notifying CFCU of the minor changes. It is accompanied by the excel template, which you can use to present your minor changes in line with Article 9(4) or when addendum is requested.

## Some frequent questions and answers:

- What is the difference between suspension and termination of grant contract?

The implementation of the action may become temporarily impossible or undesirable due to exceptional circumstances, most notably of force majeure. Under exceptional / force majeure circumstances, the Coordinator is entitled to suspend the implementation of the action or parts thereof unilaterally. The suspension of the implementation of the action implies that the beneficiaries stop carrying out the action for a specific period of time. During the suspension period the beneficiaries may only request the reimbursement of the minimum costs necessary for a possible resumption of the action. If it is practically impossible to resume the implementation of the action as initially planned then the possibility to modify the action in light of the new implementing conditions must be explored. In this assessment, it must be carefully checked to what extent an amendment of the contract is possible without putting into question the award decision or the equality of treatment. If an amendment goes against these main principles for amendments, the contract should be terminated. Suspension must lead to an extension of the duration of the action of a period equivalent to the length of the suspension (provided that the implementation can be resumed).

The contracting authority will terminate the contract or the participation of a beneficiary in any of the cases foreseen in Article 12(2) of GC. Some of these reasons are: a beneficiary(ies), or any related entity or person, have been found guilty of grave professional misconduct; a beneficiary(ies) has not fulfilled obligations relating to the payment of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which it is established; the contracting authority has evidence that a beneficiary(ies) is subject to a conflict of interests. Upon termination of this contract the coordinator shall take all immediate steps to bring the action to a close in a prompt and orderly manner and to reduce further expenditure to a minimum.

- Which intellectual property legislation is applied?

The Montenegro legislation shall be applied in all cases where the GBs are registered in Montenegro and the legislation of Albania shall be applied in all cases where the GBs are registered in Albania.

Financial Management

C H AP T E R

2

PAYMENT CLAIMS

The frequency with which pre-financing payments are made depends on the duration of the Action and on the total amount of the grant. The GC recognizes two options in Article 15(1) – Options 2 and 1. Under the 3rd CfP within the IPA CBCP MNE-ALB 2014-2020, reference number EuropeAid/171769/ID/ACT/MULTI. Option 2 will be applied.

Option 2

According to GC article 15(1)(Option 2)- for Actions which last more than 12 months and where the Contracting Authority's contribution is more than EUR 100 000, the pre-financing will be split based on several reporting periods (by default 12 months).

- An initial pre-financing payment of 100 % of the part of the estimated budget financed by the Contracting Authority for the first reporting period shall be paid upon signing of the contract. This payment will be executed without considering contingencies in the budget.

- Further pre-financing payments are split among the reporting periods (they are presented as a single global amount in the SC). If at the end of the reporting period the part of the expenditure actually incurred which is financed by the Contracting Authority is less than 70 % of the previous payment (and 100% of any previous payments), the further pre-financing payment shall be reduced by the amount corresponding to the difference between the 70 % of the previous pre-financing payment and the part of the expenditure actually incurred which is financed by the Contracting Authority.

| Project (duration 24 months, no contingencies) | Grant | Payments |
| --- | --- | --- |
| Total eligible cost = 317,648 € | 270,000 € (85%) |  |
| First instalment (first pre-financing) (100% of the part of the estimated First year budget, financed by the Contracting Authority) | 170,000 € (within 30 days) |  |
| Forecast second pre-financing | Max 73,000 € (within 60 days) | Case 1 – project reported eligible expenditures = 130,000 € (=>170,000x70%) Further pre-financing = 73,000 € Case 2 – project reported eligible expenditures = 100,000 € (58.8%, i.e. 19,000€ less than 70%) Further pre-financing = 54,000 € (73,000 – 19,000) |
| Forecast final payment | 27,000 € (within 60 days) | The balance of the final amount of the grant will only be payable after the end of the implementation period, when the final report together with a request for payment has been approved by the Contracting Authority. |

How to understand these provisions? Take for example the ‘I have a dream’ project: - they are awarded a grant contract, lasting for 24 months, total costs are 317,648 EUR and the grant is 270,000 EUR, 85%. They planned their budget in that way so that their estimate for Year One in their contracted budget is 200,000 EUR. So, upon signature of the contract, they may receive not more than 170,000 EUR (85% of their Year One planned budget). Following the 12-month implementation period they will be able to request maximum further pre-financing of 73,000 EUR.

However, in order to actually receive such amount, by month 12 they need to spend at least 119,000 EUR. Maybe they did not spend this full amount – well, then their further pre-financing is decreased, as presented in the picture above.

In your signed special conditions (Article 4), you will find info on

- Initial pre-financing, to be paid upon signature of the contract

- Further pre-financing

- Balance.

***

The contingency reserve, if it exists in budget, is not considered in the payments until, and unless, is approved (as it will not be disbursed if not needed).

Note that payment do not imply recognition of the regularity or of the authenticity, completeness and correctness of the declarations and information provided – it does not mean that the Contracting Authority has recognized your costs as eligible if they proceeded with the payment.

ACCOUNTING REQUIREMENTS

For grant contracts, the opening of new bank accounts, dedicated only to grant contract is not mandatory, and the Contracting Authority may make payments into the grant beneficiary’s general bank account (of the Coordinator of the action, not disbursed per co-beneficiaries). However, the Contracting Authority recommends, if possible and practical, to open a new account/sub-account which would enable more efficient tracking of transactions.

Article 16(1) of GC stipulates that the grant beneficiary(ies) shall keep accurate and regular accounts of the implementation of the Action using an appropriate accounting and double-entry book-keeping system.

For an expenditure in a project-dedicated accounting:

  - The debit will indicate to which category of expenditure the invoice has to be imputed

  - The credit will indicate if the invoice was paid by the beneficiary or a partner. In case of non-dedicated bank accounts, the entry should also indicate which one was used.

The accounts:

- may be an integrated part of or an adjunct to the GBs regular system;

- shall comply with the accounting and bookkeeping policies and rules that apply in the country concerned;

shall enable income and expenditure relating to the grant action to be easily traced, identified and verified.

tool 2 – Accounting systems checklist

- Convenient tool to follow

Annexed to this report you may find an Accounting Checklist (Tool 2) for your convenience.

DOCUMENTATION, FILING AND RECORD KEEPING

For the GB, keeping clear and relevant documentation is vital. Without proper documentation, it is impossible to show that the costs claimed from the CA meet the conditions of the grant contract. There must be adequate documentation proving that any expenditure is related to the project.

Based on provisions of your grant contract:

- The GBs shall keep all records, accounting and supporting documents related to the contract for five years following the payment of the balance, and in any case until any on-going audit, verification, appeal, litigation or pursuit of claim has been disposed of.

- The supporting documents and records must be easily accessible and filed in a way that, to facilitate their examination and the coordinator shall inform the contracting authority of their precise location.

- All supporting documents must be kept, such as:

  - Accounting records from the GBs accounting system such as general ledger, sub-ledgers and payroll accounts, fixed assets registers and other relevant accounting information;

  - Proof of procurement procedures such as tendering documents, bids from tenderers and evaluation reports;

  - Proof of commitments such as contracts and order forms;

  - Proof of delivery of services such as approved reports, time sheets, transport tickets, proof of attending seminars, conferences and training courses (agendas, list of participants, photos);

  - Proof of receipt of goods such as delivery slips from suppliers;

  - Proof of completion of works, such as acceptance certificates;

  - Proof of purchase such as invoices and receipts;

  - Proof of payment such as bank statements, debit notices, proof of settlement by the contractor;

  - For fuel and oil expenses, a summary list of the distance covered, the average consumption of the vehicles used, fuel costs and maintenance costs;

  - Staff and payroll records such as contracts, salary statements and time sheets.

  - Visibility material (for each kind of visibility material you must keep at least one for your archive)

Furthermore, there are certain requirements of your archiving system, as follows:

  - All transactions in accounting are referred to the necessary supporting documents;

  - The originals of the supporting documents have to be kept by each partner institution, but copies (either scanned or physical) are easily available by the Coordinator in order to facilitate the financial controls by authorized bodies. A web-based document repository shared by all partners may be very useful for this purpose;

  - The documents have to be archived in a way that they are easily accessible after the project closure. This means that each budget heading and each budget line must be separated and followed by supporting documents.

Don’t forget that the accounting records must cover all the costs of the project, irrespective of whether they have been financed by EU grant or provided by other parties, as all costs must be stated in the report.

- tool 3 – DOCUMENTATION checklist

- Convenient tool to follow

### Documentary proofs to be kept are two-fold:

Proofs for the activities implemented - The technical project documentation should be detailed enough to evidence not only the reality of the respective costs incurred, but also that the value for money principle is respected. The next table presents exemplary proofs for some of the budget headings.

| BUDGETHEADING EXPENDITURE | EXEMPLARY PROOFS OF IMPLEMENTATION / SUPPORTING DOCUMENTATION |
| --- | --- |
| 1. Human resources Staff costs | - Employment contract for employees accompanied with the Annex to the Contract (if applicable) - Monthly timesheet proving the actual time worked on the project: it has to be provided for each project team member; it must be properly filled out with a description of the tasks carried out within the project and duly signed, both by the team member and the responsible person in the employer institution. Paid leave such as national holidays and vacation must be reported regularly through total number of working hours and clearly specified in the column ‘’description of the task’’ in the timesheet - Note: If the person is working on national holiday or during the weekend without prior official approval from employer ie organization, it cannot be considered as eligible cost. Decision on the appointment of members of the project team, with specified qualification (i.e. managerial staff, technical staff, administrative staff) function in the project, to what extent the work is dedicated to the project (for examples the percentage of 100% or 20%...).. The contracts/formal nominations must be made before or at the beginning of the project for the period within the implementation dates of the project and, if necessary, can be updated during the project lifetime (i.e. adding new employee, extension of one employee’s contract, changing of the project staff members). Percentage of engagement of the staff can vary from month to month depending on the dynamic of the project, however the percentage overall project duration cannot be higher than the one initially budgeted. - Decision for annual leave (if needed) - Monthly payslips for each individual with defined gross 2 salary for total work engagement, not only for the project - Tax, surtax and contribution specifications (IOPPD forms for MNE beneficiaries; Forms for payment of taxes, surtaxes and social insurance for ALB beneficiaries are automatically generated by the Tax Office online system: web link https://efiling.tatime.gov.al/cats_public/Account/LogOn?returnUrl=%2Fcats_public)%2FPayrollV2%2FDetail%2F14243941). ). - Evidence of payment of salaries and payment of taxes, surtaxes and contributions (bank statements, confirmation of executed order, etc.). |
| 1. Human resource Per diems | - Program of the seminar/event; - Proof of event happened and proof of participation (signed list of participants, agenda, photos, minutes, travel report); - Travel order - with clearly specified date and time of travel, certifying the mission carried out, from which it is clearly possible to infer the name of the travelling employee(s), date, reason and destination of the mission; - Proof of travel happened (e.g. travel receipts, bus/train/flight ticket, hotel invoice, boarding pass for each flight, copy of passport entry/exit...) - Proof of payment of costs directly paid by the institution or in case of cost directly paid by the employee proof of payment by the employee and proof of reimbursement to the employee by the institution. - Internal regulation regarding the travel costs (per diem, fuel etc) for travels within Albania or abroad. |
| 2. Travel | - Duly filled and signed order for the mission; - Individual report on the mission and materials of the mission (invitation, agenda, list of participants, description of the individual contribution etc.); - Public transport: Transport tickets; - Log book that proves mileage on the car. - Car: For fuel and oil expenses, a summary list of the distance covered, fuel costs - Proof of payment of costs directly paid by the institution or in case of cost directly paid by the employee proof of payment from the employee and proof of reimbursement to the employee by the institution (e.g., bank statement). |
| 3.Equipment/supplies | - Procurement documents (tender dossier, tender evaluation report and respective annexes, technical acceptance form); - Copies of submitted offers - Copy of the supply contract - Copy of the Certificate for origin (if applicable) - Copy of the inventory register - Protocol for transferring the ownership(if applicable) - Invoice – with clearly stated number/name of the project - Proof of payment such as bank statements - Copy of Certificate for VAT exemption |
| 4. Local office (only when need for setting up or using a project office is recognised by the Contracting Authority in the Special Conditions) | - Contract for renting the office - Proofs about the proportion in which the office is used for the project (if applicable) - Invoices - Proof of payment such as bank statements. |
| - 5. Other costs, services | - Procurement documents (tender dossier, tender evaluation report and respective annexes, service provision report(s); evidence of experts’ selection process (invitation letter/call), CVs, Terms of Reference, report of the selection committee etc.); - Copies of submitted offers (for beneficiaries registered in Albania: at least three offers to show market research if expense is less than 2,500 Euro); - Contract of the service contract; - Program of the conference; - List of participants; - List of trainers/lecturers; - Materials; - Contributions; - Publications; - Photos and/or video records of the events; - Feedback questionnaires; - Invoice/receipt – with clearly stated number/name of the project - Proof of payment NOTE: Costs will only be reimbursed if supporting documents (visibility materials, presentations, labels on purchased equipment, etc.) respect all EU visibility rules. |
| - 6. Other - Works - (or any other cost planned under this BH) | - Procurement documents (tender dossier; tender evaluation report and respective annexes; work acceptance form) - Copies of submitted offers - Copy of the work contract - Invoice/receipt – with clearly stated number/name of the project; - Proof of payment. |

UNDERSTANDING ELIGIBILITY OF COSTS

- Eligible costs are actual costs incurred by the Grant Beneficiaries, which meet all the eligibility criteria at the same time, and do not fall under the category of ineligible costs. Furthermore, they must be in line with the specifications included in the call for proposals, which may provide for specific instructions and/or limitations to the general rules set in the GC (if appropriate, specific clauses will also be included in the SC).

- Costs have to be related to and generated by activities carried out within the implementation period of the action and in accordance with the contract.

- To be considered eligible, costs must be actually incurred by the beneficiaries, and must have generated a debt to be paid directly by an entity, which is party to the contract with the Contracting Authority (i.e. the Coordinator or a co-beneficiary).

- It is worth reminding that costs that might have been deemed eligible at a first glance in the reports may be declared ineligible following an audit or verification carried out.

## Eligibility criteria

The following table brings some assistance in further understanding eligibility criteria for the costs of the action.

| ELIGIBILITY CRITERIA | HOW TO UNDERSTAND THIS | DETAILS |
| --- | --- | --- |
| Costs are incurred during the implementation of the action | - costs relating to services and works shall relate to activities performed during the implementation period. costs relating to supplies shall relate to delivery and installation of items during the implementation period. - costs incurred should be paid before the submission of the final reports. They may be paid afterwards, provided they are listed in the final report together with the estimated date of payment | - an exception is made for costs relating to final reports, including expenditure verification, audit and final evaluation - Any amount above EUR 500 that is unpaid on the date of submission of the final reports has to be clearly listed in the 'List of Pending payments' in the final financial report - Contract-award procedures may be initiated before the start of the implementation period, in accordance with the rules set forth in Annex IV of the grant contract. This allows for instance for the signature of a procurement contract before the start of the action in order to be already operational when the action starts. However, the respective costs will have to be generated (i.e. incurred) during the implementation period of the action in order to be eligible. |
| They are indicated in the estimated overall budget of the action | In principle, only those cost items that have been approved in the budget and the description of the action are eligible, although it is possible to remove a budget item or introduce a new one. A request for amendment to the contract may have to be submitted by the Coordinator according to Article 9. |  |
| They are necessary for the implementation of the action | It is important to pay particular attention to explain which specific resources and related costs are needed for the implementation of the action, in order to justify their link with the action (activities, results and objectives) and therefore their funding. Costs for items charged that were not necessary for the project purposes are a frequent source of cost ineligibility. | Explanations can be implicitly done in the description of the action, but more specifically it also has to be included in the budget, in Worksheet 2. |
| They are identifiable and verifiable, recorded in the accounting of beneficiary and partners, and backed-up by originals of supporting documents | All the costs incurred - corresponding to the entire budget of the action and not only to the EU grant - must be recorded in the accounts of the beneficiaries or, as the case may be, of the affiliated entities. The supporting documents (tenders, orders, vouchers, invoices, receipts etc.) must be in place and tally with the recorded costs. |  |
| They are compliant with the requirements of applicable tax and social legislation | The beneficiaries and the affiliated entities are fully responsible for the Coordination and execution of all activities and have to ensure compliance with local, national and other applicable legislation. | Salaries: costs of staff shall include social security charges and other remuneration costs. Beneficiaries to provide proof of payment of these costs. Equipment and external services – VAT exemption procedure to be implemented or VAT reimbursement for Albanian partners |
| They are reasonable, justified and comply with the requirements of sound financial management, in particular regarding economy and efficiency | It is important to pay particular attention to explain how costs are calculated and budgeted. This is particularly true for those costs that are not easily justifiable because, for instance, they are especially high (compared to other similar items) and/or are purchased in high quantity. | The explanation has to be provided at proposal stage in the budget, worksheet 2, in the column 'justification of the estimated costs', and/or as appropriate in the description of the action and the reports to understand their relationship with the results/activities of the action. |

## Types of costs by nature

Coordinators and staff tasked to implement the action, should be familiar with different types of costs related to grant funds. The following table brings some more information.

| Types of costs | What are they | DETAILS |
| --- | --- | --- |
| Direct Eligible Costs | The following direct costs of the beneficiary(ies) shall be eligible: - the cost of staff assigned to the action, corresponding to actual gross salaries including social security charges and other remuneration-related costs (excluding performance-based bonuses); - travel and subsistence costs for staff and other persons taking part in the action, provided they do not exceed those normally borne by the beneficiary(ies) according to its rules and regulations. - purchase costs for equipment and supplies (new or used) specifically dedicated to the purposes of the action, provided that ownership is transferred at the end of the action when required - depreciation, rental or leasing costs for equipment (new or used) and supplies specifically dedicated to the purposes of the action - rental costs related to project office, when a project office is foreseen, duly justified and described in the description of the action and in the special conditions - costs of consumables - costs of service, supply and work contracts awarded by the beneficiary(ies) for the purposes of the action - costs deriving directly from the requirements of the contract (dissemination of information, evaluation specific to the action, audits, translation, reproduction, insurance, etc.) including financial service costs (in particular the cost of transfers and financial guarantees where required according to the contract) - duties, taxes and charges, including VAT, paid and not recoverable by the beneficiary(ies), unless otherwise provided in the SC: | - Salaries and costs shall not exceed those normally borne by the beneficiary(ies), unless it is justified by showing that it is essential to carry out the action - As a general rule, tasks performed by consultants, experts and/or other service providers (e.g. accountants, lawyers, translators, external IT staff, etc…) are to be considered as resulting from implementation contracts - Consultants are not considered as human resources (budget heading 1) but as other costs/services (budget heading 5 or 6) - The rates of per diems per country published by the European Commission at the time of contract signature may never be exceeded. Also note that GBs should have their own internal rulebooks stipulating amounts and payment procedures for per diems and if not, national Ruling should be used. - Travel by plane must be always in economy class, unless at the moment of purchase business class was not more affordable in which case proofs of this situation should also be provided. - The costs of supply, service or work contracts should be awarded in line with the procurement rules set out in Annex IV of the grant contract - Supplies may originate from any country if the amount of the supplies to be procured is below 100.000 € per purchase (or per lot, if the procedure is divided into lots) - As a general rule beneficiary have to apply for tax (including VAT) exemption whenever possible. For the beneficiaries registered in Montenegro CFCU has a dedicated manual on VAT exemption on their webpage http://www.cfcu.gov.me/vijesti/156867/Nove-instrukcije-za-oslobadanje-od-placanja-PDV-a-decentralizovano-indirektno-upravljanje.html Template for VAT Exemption request for MNE beneficiaries is available under Tool 11. For the beneficiaries registered in Albania, the Ministry of Finance and Economy of the Republic of Albania published, the new Instruction "ON A MODIFICATION OF THE INSTRUCTION NO. 6, DATED 30.01.2015 "ON THE VALUE ADDED TAX IN THE REPUBLIC OF ALBANIA" on the Official Gazette No. 169 of the Republic of Albania on the 11 December 2019 which can be found on the website of the General Directorate of Taxation of the Republic of Albania https://www.tatime.gov.al/c/6/378/379/tatimi-mbi-vleren-e-shtuar. The necessary forms for the procedure are available at the following link: https://www.tatime.gov.al/d/8/129/209/185/tatimi-mbi-vieren-e-shtuar |
| Simplified Cost Option | Where possible and appropriate, lump sums, unit costs or flat rates shall be determined in such a way as to allow their payment upon achievement of concrete outputs and/or results. Costs declared under simplified cost options shall satisfy the eligibility criteria set out in Article 14(1) and 14(2) of the GC. They do not need to be backed by accounting or supporting documents, save those necessary to demonstrate the fulfilment of the conditions for reimbursement established in Annex I and III of the Grant Contract and Annex K published at the time of the Call for Proposals. | - The amounts or rates of unit costs, lump sums or flat rates set out in Annex III (in case of simplified costs option) may not be amended unilaterally and may not be challenged by ex post verifications. - These costs may not include ineligible costs as referred to in Article 14(9) of the GC or costs already declared under another costs item or heading of the budget of this contract. - Simplified cost options that are not result based shall not be authorized unless they have been ex ante assessed. |
| Contributions in kind | Any contributions in kind, which shall be listed separately in Annex III, do not represent actual expenditure and are not eligible costs. Unless otherwise specified in the SC, contributions in kind may not be treated as co-financing by the beneficiary(ies). If contributions in kind are accepted as co-financing, the beneficiary(ies) shall ensure they comply with national tax and social security rules. | - If the description of the action provides for contributions in kind, such contributions have to be provided |
| Volunteers' work | The value of the work provided by volunteers can be recognised as eligible cost of the action and may be treated as co-financing by the beneficiary(ies) | - This type of costs must be presented separately from other eligible costs in the estimated budget. The value of the volunteers’ work must always be excluded from the calculation of indirect costs. |
| Contingency reserve | Can only be used in case of unforeseeable changes of circumstances • Can only be used with prior approval by CA ;not exceeding 5 % of the direct eligible costs | - The contingency reserve should only be included in the initial total Budget, and not budgeted in the requests for pre-financing - The contingency reserve cannot be modified through Notification letter - No accounting entries will be found under this category |
| Eligible indirect costs | This category is described in Article 14(7) of the GC; They are calculated as a fixed rate (max 7%) of the total amount of direct eligible costs | - The flat rate does not need to be supported by accounting documents - These costs cannot be modified through Notification letter. |
| Ineligible costs | According to the general template of the GC: debts and debt service charges (interest);b) provisions for losses, debts or potential future liabilities; costs declared by the beneficiary(ies) and financed by another action or work programme receiving a European Union grant (including through the European Development Fund);purchases of land or buildings, except where necessary for the direct implementation of the action and according to the conditions specified in the SC; in all cases the ownership shall be transferred in accordance with Article 7(5), at the latest at the end of the action; e) currency exchange losses; credits to third parties, unless otherwise specified in the SC; in kind contributions (except for volunteers' work);salary costs of the personnel of national administrations, unless otherwise specified in the SC and only to the extent that they relate to the cost of activities which the relevant public authority would not carry out if the action were not undertaken; performance-based bonuses included in costs of staff | - SC may derogate some of these. |

In order to further support GBs – a template for the monthly timesheet is provided in tool 4.

tool 4 – TIMESHEET

- Convenient tool to follow

Secondary Procurement

C H AP T E R

3

Rules for procurement are defined in ‘Annex IV Procurement by Grant Beneficiaries in the context of European Community external actions’ annexed to the grant contract. This Annex is applicable to the GBs and all partners, as well as affiliated entities, regardless of their legal status (public or private) or nationality.

For what is NOT described in Annex IV (detailed procedures, tender documents) you may:

  - Either use your own procedures, that must be in accordance with Annex IV rules,

  - Or may use Chapters 3 (Service), 4 (Supply), 5 (Works) of PRAG and related annexes.

Whatever system of procedures is chosen, it must be consistently throughout project implementation, i.e. combination of “own procedures”(or national) and PRAG procedures for different secondary procurements under the same contract is not advised.

Note that the Grant Beneficiaries and Associates are not eligible for sub-contracting. This means that you cannot procure an organization X to provide you a certain service, if that organization is identified as a Co-beneficiary/Associate in your grant action.

## What is PRAG

The practical guide on contract procedures for European Union external action (PRAG) provides Contracting Authorities, on the one hand, and tenderers, candidates, applicants and contractors, on the other hand, with practical assistance in preparing and implementing procurement and grant contracts in the field of external action. Although the PRAG provides explanations and information strictly in compliance with the rules and regulations in force, it is not legally binding.

PRAG does not apply to Grant Beneficiaries for which Annex IV of the standard grant contract applies (as defined by Scope of PRAG, section 1.2). However, Annex IV of your grant contracts also states that: “The beneficiary may decide to apply the procurement procedures set forth in the practical guide. If these procedures are correctly followed the principles above will be deemed to be complied with.” In this sense, if you do not have standardised approaches or practices in relation to procurement, the use of PRAG is recommended.

Under the 3rd CfP within IPA CBCP MNE-ALB 2014-2020, reference number EuropeAid/171769/ID/ACT/MULTI, the PRAG 2020 version is applied and may be found at the following site:

https://wikis.ec.europa.eu/display/ExactExternalWiki/ePRAG.

Regardless of whether you follow PRAG or not, Annex IV obliges you to follow certain principles:

Principle 1 - Best Value for Money

If the implementation of an action requires procurement by the beneficiary(ies), the contract must be awarded to the tender offering best value for money (i.e. the tender offering the best price-quality ratio) or, as appropriate, to the tender offering the lowest price.

Principle 2 - Avoidance of conflict of interest

The beneficiary(ies) shall avoid any conflict of interests.

Principle 3 - Being able to justify the choice of tenderer

Where the beneficiary does not launch an open tender procedure, it shall justify the choice of tenderers that are invited to submit an offer.

Principle 4 – Using objective criteria in evaluation

The beneficiary shall evaluate the offers received against objective criteria which enable measuring the quality of the offers and which take into account the price (the offer with the lowest price shall be awarded the highest score for the price criterion).

Principle 5 – Record keeping

The beneficiary shall keep sufficient and appropriate documentation with regard to the procedures applied and which justify the decision on the pre-selection of tenderers (where an open tender procedure is not used) and the award decision.

Principle 6 –Respecting EU restrictive measures

With reference to Section 2.4 of PRAG, the beneficiary shall be responsible for the respect of EU restrictive measures in the award of contracts. The lists of persons, groups, entities subject to the EU restrictive measures are maintained by the Service for Foreign Policy Instruments and published on the following website: www.sanctionsmap.eu

Note that failure to comply with these principles or rules would render the related expenditure ineligible.

Eligibility of secondary procurement contracts is also defined – in terms of rules of nationality and rules of origin. Only in duly substantiated exceptional cases, and not just because a product of ineligible origin is cheaper than the EU or local product may these rules be exempted from, and this needs to take place by derogation only! (derogation is requested from the CFCU).

## Nationality

Award of procurement contracts is open to all natural and legal persons of Member State or a country, territory or region mentioned as eligible by the relevant regulation/basic act governing the eligibility rules for the grant - art. 10 of the IPA regulations (Regulation EU – 236/2014). Tenderers must state, in the tender, the country of which they are nationals by presenting the usual proof of nationality under their national legislation.

This rule does not apply to experts proposed by service providers taking part in tender procedures or service contracts financed by the grant.

## Origin

Note that under IPA II (and IPA CBCP MNE-ALB 2014-2020 is a part of IPA II) supplies may originate from any country if the amount of the supplies to be procured is below 100.000 € per purchase (in cases of supply tender divided into lots, this means per lot). Where supplies may originate from any country, no certificate of origin needs to be submitted. * The amount tendered must be as planned in the project budget.

In awarding contracts, certain principles should be taken into account:

  - Transparency - the amount of information to be provided on orders and procedures, and the publicity of the actions/inactions of the Contracting Authorities on selection of a contractor;

  - Proportionality - required award criteria are proportional and appropriate to the objective of the procurement;

  - Equal treatment - all candidates in procurement processes are subject to exactly the same conditions for submission and evaluation of tenders and are treated in exactly the same way;

  - Non-discrimination - prohibits discrimination based on preferences due to nationality of the suppliers and producers –e.g. local tenderers at the expense of foreign ones.

#### Common rules applicable to all tender procedures

- Beneficiary - acts as Contracting Authority (in the following text the function of the Contracting Authority will be assigned to the Grant Beneficiary) and is responsible for issuing invitations to tender, receiving offers, chairing tender evaluation committee, deciding on the results of the tender procedure, awarding to and signing the contract with the successful tenderer;

- The time-limits for receipt of tenders and requests to participate must be long enough to allow interested parties a reasonable and appropriate period to prepare and submit their tenders.

- All requests to participate and tenders declared as satisfying the requirements must be evaluated and ranked by an evaluation committee on the basis of the exclusion, selection and award criteria announced in advance. This committee must have an odd number of members, at least three, with all the technical and administrative capacities necessary to give an informed opinion on the tenders. Note however that, in cases of single tenders, according to PRAG (section 2.6.8 – ‘When the contract does not exceed EUR 20 000 appointing an evaluation committee is never mandatory.’ – in these cases you will appoint the persons to take part in negotiations.

- Do not split artificially the contracts to circumvent the procurement thresholds as all the amount may become ineligible.

There are several types of contract you may need to procure:

- Service contracts: Studies: identification and preparation of projects, feasibility studies, economic and market studies, technical studies, evaluations and audits, engagement of external experts, etc.

- Supply contracts: Purchase, leasing, rental or hire purchase (with or without option to buy) of equipment

- Work contracts: execution, or execution and design, of works or the realization, of a work corresponding to the requirements specified by the contracting authority.

tool 5 – single tender ’packages’ and simlified procedure‘package’

- Convenient tool to follow

You may need to follow Single Tender Procedure or Simplified Procedure in most cases. The templates are provided in Tool 5.

- Under the simplified procedure, the Contracting Authority invites at least three candidates of its choice to submit tenders.

- Contract may be awarded directly in the following circumstances:

  - using the 'single tender procedure' when the contract does not exceed EUR 20 000;

  - using the 'negotiated procedure' whatever the value of the contract in exceptional and duly justified cases. No specific threshold applies in such cases.

tool 6 – PROCUREMENT PLAN TEMPLATE

- Convenient tool to follow

The Grant Beneficiaries are recommended to prepare after the beginning of the project implementation a procurement plan (at the latest by the end of the first month of implementation), which indicates all of their planned procurement procedures. The template is provided in Tool 6.

Financial support to third parties

It may happen that the implementation of the action involves the award by beneficiaries of financial support to third parties (FSTP). The persons/entities receiving FSTP are the final recipients of the EU funds.

This is allowed provided that the objectives or results to be obtained are clearly detailed in the description of the action and that all the following conditions are fulfilled:

1) The contracting authority has verified that the coordinator offers adequate guarantees as regards the recovery of amounts due. Indeed, in the event of a recovery order at the end of the action, the contracting authority exclusively turns to the coordinator, who then may be asked to reimburse amounts that beneficiaries or affiliated entities have unduly transferred as FSTP.

2) Beneficiaries may not exercise any discretionary power in granting FS to third parties. In order to ensure this, the guidelines for applicants require that the proposals include:

- a fixed and exhaustive list of the different types of activities for which a third party may receive FS,

- the definition of the persons or categories of persons that may receive FS,

- the criteria for awarding FS,

- the maximum amount to be granted to each third party and the criteria for determining it.

In all events, these elements have to be specified in the contract (notably in the description of the action).

For further information on FS to third parties see section 6.8.2 of the Practical Guide.

3) Beneficiaries must ensure that recipients of FS allow the contracting authority, the Commission, OLAF, and the Court of Auditors to exercise their powers of control on documents, information, even stored on electronic media, or in the recipient’s premises.

For FSTP, the beneficiaries are fully responsible for the implementation of the action in compliance with the contract. If the conditions set out in the contract for FSTP are not fulfilled, the corresponding costs incurred by the beneficiaries will not be eligible.

Example: FS is, in accordance with the contract, to be given to local NGOs for teaching activities. The funds received as FS are used by local NGOs for their own promotion. The FS given by the beneficiary is ineligible, the funds incorrectly used will be recovered by the contracting authority from the coordinator (regardless of who is at fault and of whether the coordinator decides to recover that money from the local NGOs or not).

Finally, beneficiaries cannot be exempted from their responsibility on the basis of the argument that the action was not properly implemented due to a failure by the recipients of FS.

FSTP is an activity carried out within the contract, and may be implemented by all beneficiaries, as well as affiliated entities, provided that the mandatory conditions stated in the contract are fulfilled. Indeed, the cost eligibility conditions applicable to affiliated entities are the same as those applicable to the beneficiaries. So they may award FS to third parties under the same conditions as beneficiaries (i.e. on the condition that all the minimum elements required in the Description of the Action are respected).

It is essential for the eligibility of FS, that all these mandatory conditions are strictly defined in the contract (notably in Annex I), in compliance with the guidelines for applicants and with any conditions or restrictions set out regarding:

(i) the objectives and results to be obtained with the financial support

(ii) the different types of activities eligible for financial support, on the basis of a fixed list

(iii) the types of persons/entities or categories of persons/entities that may receive financial support

(iv) the criteria for selecting these persons/entities and giving the financial support

(v) the criteria for determining the exact amount of financial support for each third party, and

(vi) the maximum amount that may be given.

Keep in mind that the FSTP is justified if given to support the achievement of the objectives of the action.

The FSTP has to be necessary for the implementation of the action, and embedded in its design.

The FSTP must be clearly identifiable in the budget under Heading 6 ‘Other’.

Grant beneficiaries must ensure that recipients of financial support to third parties, do not include entities/persons included in the lists of EU restrictive measures.

To the extent relevant, the beneficiary(ies) shall ensure that the conditions applicable to them under Articles 3, 4.1-4.4, 6 and 16 of general conditions are also applicable to third parties awarded financial support.

Monitoring, Evaluation, Compliance

C H AP T E R

4

Planning, monitoring and evaluation come together as Results Based Management (RBM) aimed at achieving improved performance and demonstrable results. RBM implies a shift from inputs to results and is a set of iterative steps aimed at ensuring the attainment of the desired change. IPA II, which IPA CBCP MNE-ALB 2014-2020 is a part of, is strongly embedded in this shift. RBM is a management strategy by which all actors, contributing directly or indirectly to achieving a set of results, ensure that their processes, products and services contribute to the achievement of desired results (outputs, outcomes and impact). The six steps of the RBM include:

According to OECD, monitoring is a continuing function that uses systematic collection of data on specified indicators to provide management and the main stakeholders of an on-going intervention with indications of the extent of progress and achievement of objectives and progress in the use of allocated funds.

Evaluation is the systematic and objective assessment of an on-going or completed action or policy, its design,

implementation and results.

- Clearly identifying program beneficiaries and designing programs to meet their needs.

- Defining realistic expected results, based on appropriate analysis.

- Identifying and managing risks.

- Monitoring progress towards results with the use of appropriate indicators.

- Increasing knowledge by learning lessons and integrating them into decisions, and

- Reporting on results achieved and the resources involved.

Within your grant actions – you will monitor actions internally, and you may commission an external evaluator to help you understand change you have/not produced. Externally, you will be monitored by the JTS (JTS staff can be accompanied by the staff of the OSs or the CA, as appropriate) through monitoring visits and your compliance with the grant contracts shall be verified by CFCU, through on the spot verifications.

## Internal M&E

According to Article 8(1) of GCs GBs have to include all the monitoring and evaluation (M&E) arrangements in their description of the action. The logic of intervention, your log frame matrices, articulate the pathway to change under your grant actions - clear definition of results, measurable indicators and systematic M&E arrangements are key factors of success. Results? These are outputs, outcomes and impact as defined in your log-frames, as the result chain. In simple terms, it is about monitoring risks and monitoring progress towards results.

Take for example the diagram on the left – if shows you links between your results and risks:

- On the level of inputs (this is your budget) you may encounter financial management risks.

- On the level of output, you may encounter implementation risks. You may not be able to contract a proper trainer. You may be in delay in production of certain outputs.

- Finally, on the level of outcomes, you may encounter programme design risks – perhaps you action is not producing the change as desired, due to wrong methodology. If this is the case – well, then you have to rethink.

- On the level of impact, while there are risks, they relate to policies that are often outside you.

Bear in mind – you are bound by your log frames that are the part of the contract. No baselines, no possibility to see the change. No source of data, no possibility to inform the indicators. Hence, if there is something at fault with your log frames, you must revise them. If not, data collection throughout the action is the key.

Internal monitoring process:

- tracks the actual performance or situation against what was planned or expected according to pre-determined targets,

- highlights the strengths and weaknesses in project implementation enabling managers to deal with the problems, find solutions and adapt to changing circumstances in order to improve the projects performance,

- provides an “early warning system”, which allows for timely and appropriate intervention if a project is not in line with the initial plan,

- ensures adequate risk assessment and establishes timely prevention and/or mitigation measures.

Before the project implementation starts, all project partners should be informed that monitoring will take place during course of the project.

Monitoring answers to the What question bringing alerts & allowing identification of corrective measures. Evaluation answers the Why question.

The following table can help you distinguish between monitoring and evaluation.

|  | Monitoring | Evaluation |
| --- | --- | --- |
| Objective | To identify implementation problems To assess the progress towards objectives | Learning and accountability To assess actual outcomes and impacts |
| Timing | Continuous, all along the intervention’s duration. It produces data in time series. | In specific moments of the intervention’s cycle |
| Users | GBs, CA, CBC Bodies, Control Body and JTS | GBs, CAs, CBC Bodies, Control Body, JTS, stakeholders |
| Responsibilities | Operational staff and/or external monitors | Internal and/or external evaluators |
| Focus | On implementation: Interventions’ progresses and first results. Inputs, activity execution, delivery of outputs and contribution to the achievement of outcomes Efficiency and effectiveness Key question: What is the intervention doing and how far is implementation is progressing? | On results: Outcomes and intermediate and long-term impacts. Strategic aspects (relevance, coherence, EU added value) and sustainability Explores unintended results Key question: To what extent and why is the intervention producing (or failing to produce) the specific outcomes and impacts which have materialised—be those negative or positive? |
| Methods | Greater emphasis on quantitative indicators Output and process indicators Quick exercise gathering data from systematised internal systems but also external missions | Greater emphasis on qualitative indicators Outcome and impact indicators More rigorous and sophisticated exercise, gathering data emerging from primary data sources, such as research |
| Reports | Standard and comparable formats Report progress | Less standardised presentation, In-depth analysis on selected issues linked to the achievements of intended objectives Provide lessons and recommendations |
| Dissemination | Limited | Wider |

Note that, if you had planned external evaluation under the grant action, all mid-term and final evaluation reports produced throughout the action have to be shared with the CA.

## External Monitoring/Compliance verifications

During the external monitoring/compliance verification process; the following aspects of quality implementation are taken into account:

  - The Procedures: Compliance with procurement rules, eligibility of costs, visibility, documentation, archiving, bookkeeping, accounting and reporting requirements, contract modifications rules. The results are non-compliances and irregularities identification.

  - Progress: Monitoring of progress against grant contract results and grant scheme results.

  - Problems encountered: financial and procurement related issues, administrative problems, technical difficulties in implementation.

While CFCU conducts ‘on-the-spot verifications’ (potentially accompanied with CB, CBC Bodies and JTS), ‘monitoring  visits’ are conducted by JTS (JTS staff can be accompanied by the staff of the OSs or the CA, as appropriate).

On-the-spot Verifications

OTSCs are conducted by the CFCU to the Montenegrin beneficiaries and by CB to Grant beneficiaries from Albania (CFCU can decide to join the OTSCs to Albania beneficiaries as well) at key time moments, such as upon submission of reports. Minimum of 2 scheduled visits are planned to each grant action, within the implementation/execution period. Number may change depending on the identified project’s risks and nature of such risks. The schedules of OTSVs are agreed with the Coordinator. The on-the-spot verifications will be officially announced to the Coordinator at least ten days before the visit shall take place. During these verifications, project documentation is thoroughly examined, verification of the physical existence of the equipment procured is done, quality of the implementation of the activities is assessed and compliance with the secondary procurement procedures also takes place. Joint OTSCs of CFCU and CB may also be performed. These on the spot checks may be organized in cooperation with JTS. The following table reveals some of the issues that are checked.

Major Items to be checked during the on-the-spot verification

PREPARATION

Original copy of the contract available Original copy of addenda (if applicable) available

DOCUMENTS VERIFICATION

Availability of produced documents, confirming that activities are in progress and/or completed If there have been changes to the nature of the activities, have they been reflected in addenda/notification if necessary

COST VERIFICATION

Availability of invoices and/or other supporting financial documentation confirming the completion and/or progress of activities.

VISIBILITY

Are all visibility requirements fulfilled according to the contract

#### Tips for successful on-the-spot VERIFICATIONS:

- Have a meeting with key staff and partners to prepare for the visit;

- Have your records and documentation organized;

- Be prepared to briefly explain the status of each project activity;

- Calculate your spending and compare with initial plans;

- Do not forget to mention if you experience any problems and/or have encountered any financial issues;

- Present the status of your procurement procedures against your Procurement.

- Be aware of visibility requirements which must be fulfilled.

### Ad-hoc visits

These visits are carried out with prior notification and aim at assessment of specific project implementation aspects: risk management, collection of additional information; verifying if information on the spot corresponds with the information received by the CFCU and the JTS.

### Monitoring visits:

JTS will be conducting monitoring  visits. They shall focus on assessing the progress of your action – against results contracted, and against quality defined in proposal. Namely, the purpose of the monitoring visits is to assess the quality of implementation of the project in terms of relevance, effectiveness, efficiency, sustainability, impact & cross-border effect, coherence & complementarity and community added value. The monitoring visits will review the progress of project activities to date, progress towards stated project objectives and outputs/results, quality of project management, performance of secondary procurement and document management, compliance with visibility rules, any irregularities or problems and future sustainability.

Some of the issues checked at OTSPs may be the same. Some, on the other hand, may serve to ascertain sustainability of the action. For example, below are some of the issues that may be the focus on these visits:

Major items to be checked during the monitoring visits

PREPARATION

Copy of the contract available Copy of addenda (if applicable) available

PROJECT PROGRESS (Efficiency, Effectiveness and Impact)

Are the activities being implemented in line with the description of the action and timetable of activities? Are activities being implemented within the budget envisaged? If there have been changes to the nature of the activities, have they been reflected in addenda/notification if necessary Are the outputs/results (if indicated) of the project being achieved in line with the contract Do the grant beneficiaries use log-frame indicators in order to assess project progress against indicators? Will the project contribute to the Programme indicators? Are the specific objective(s) of the project achieved

VISIBILITY

Are all visibility requirements fulfilled according to the contract

SUSTAINABILITY

Outputs/results of projects are still in use Studies/analysis which are developed through the project are <in process of adoption or they are adopted> or <are in process of incorporation or they are incorporated in the relevant legal act(s)>, in accordance with national legislation Equipment is maintained and in use Works constructed under the project are maintained and in use

Reporting

C H AP T E R

5

As a part of your grant contacts, in Annex VI, you are provided with the templates for interim and final reports. The narrative and financial reporting is described in Article 4 of the SC of the contract and complemented by Article 15.(1) to 15.(5) of GC explaining the conditions for payment claims and the documents to attach. In addition, according to Article 4.3 of the SC of the contract, reports on the achievement of indicators shall be submitted quarterly. Important templates therefore to consider are:

- Annex V to contract: model of payment request (to be sent alongside interim and final reports) and

- Annex VI to contract: model narrative and financial report and

- Annex VII to contract: model of expenditure verification report

- List of indicators MNE-ALB that presents the achievement of the performance indicators for the IPA CBC MNE-ALB 2014-2020

The period covered by the narrative report matches with the period covered by the financial report. This period should be clearly stated in the reports. The reports, both narrative and financial, (as well as expenditure verifications and detailed breakdown of expenditure, where applicable) must cover the whole action as it was presented in the application and accepted by the Contracting Authority, not only the share financed by the EU contribution.

Also, bear in mind that, the Coordinator must provide an expenditure verification report for: any final report in the case of a grant of more than EUR 100 000. The expenditure verification report shall conform to the model in Annex VII of the grant contract and shall be produced by an auditor approved by the Contracting Authority. The auditor shall meet the requirements set out in the Terms of Reference for expenditure verification in Annex VII.

The purpose of reports is to explain:

- the results achieved and the related costs identified in the financial report

- the deviations that may have occurred (possibly subject to an amendment in accordance with Article 9) as compared to the initial proposal with regards to results and to means and costs.

Each narrative report also includes an updated logical framework matrix. The logframe matrix presented for the description of an action is updated for reporting purpose by adding one column providing the actual value of the results indicators for each relevant level of the chain of the results (Current value, marked yellow in the table below). Any necessary update/modification of the targets, baselines, sources of verification related to these indicators should be made in the same log-frame matrix with due consideration to the rules for amendments.

|  | Results chain | Indicators | Baseline (incl. reference year) | Current value DATE OF REPORT | Targets (incl. reference year) | Sources and means of verification | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Overall objective: Impact |  |  |  |  |  |  |  |
| Specific objective(s): Outcome(s) |  |  |  |  |  |  |  |
| Outputs |  |  |  |  |  |  |  |
| Activities |  |  |  |  |  |  |  |

It is important that the 'focus on results' be kept in mind when preparing the reports, in order to provide information on the type of costs incurred and to understand their relation with the results/activities of the action.

- Each Interim report (narrative and financial), covering the elapsed reporting period (12 months) shall be submitted within 60 days following the end of the reporting period (so 12 months plus maximum 60 days). If you are, for whatever reason unable to submit report in due time, you should inform the Contracting Authority of the reasons and provide a summary of progress of the grant action.

- The Final report has to give an overview of last period's implementation and of the action as a whole for all its duration. The final report must always include a detailed breakdown of expenditure covering the whole action and, in addition, an expenditure verification report if requested in accordance with Article 15(7) of GC. The information on transfers of ownership (where applicable) has to be provided using the template in Annex IX. The copies of the proofs of transfers have to be attached according to Article 7(5).Final reports shall be sent within 3 months after the end of the implementation period (as defined in Article 2 of the SC).

- The list of indicators that the applicants had to include to estimate the project’s contribution to the programme’s objectives refer to impact, outcome and output indicators as provided within the Guideline for applicants for this CfP. Applicants shall according to the provisions of the Article 4.3 of the special conditions of the grant contract quarterly report on the achievement of indicators. These reports will be submitted at regular intervals on 31 March, 30 June, 30 September and 31 December every year and then upon the submission of the final report. These reports will be submitted to the JTS of the programme (to Project officer of their project) following a specific template to be provided by the JTS by email no later than 2 weeks after the expiration of each quarterly period.

## Narrative report

When reporting on progress against results, you will be using interim/final narrative report. The sections that need to be filled are the following: Executive summary of the Action; Results and Activities; Log frame; Contracts above € 60 000 awarded; Updated action plan for the future activities of the project (interim report only); Beneficiaries/affiliated entities and other Cooperation; and Visibility.

## Financial report

When reporting on the costs incurred/spent, you shall be using the financial report.

The financial reports must have at least the same level of detail as the budget annexed to the contract. Any relevant variation from the budget initially submitted must be explained. The financial reports must be consistent with the records, accounts, and ledgers of the beneficiaries and affiliated entities.

Interim financial report – includes the following sheets, that ask you for the stated information, for example:

In forecast budget and follow up:

- Use Columns A to E, for budget for the 1st year of the project implementation as per the contracted budget;

- Use Column F to present real costs incurred in the reporting period;

- Use Columns G to J – to present expected budget for the remaining implementation period of the project.

In the sheet for Interim report:

tool 7 – REPORTING templates (Interim and final narrative and financial)

- Convenient tool to follow

- Columns A to E, present the budget as per the contract or last addendum signed;

- Column F – presents the modifications of the budget approved by the CA with an No objection i.e. modifications <25% (+/- xxxx EUR);

- Columns G to I– present expenditures incurred –insert the costs incurred during the reporting period;

- Column  J – insert the costs incurred during the period before reporting period;

- Column K – insert the formula which represents the cumulative amount of column I and column J.

Attached to these Guidelines – you may find Tool 9– Reporting checklist which you may use while preparing your reports. In addition, you may find template for cover letter for submission of the report to the Contracting Authority and Control Body.

Copies of invoices, contracts or order supporting documenting justifying the expenditure made have to be attached to the reports (including interim and final). Also, copies of studies, evaluations, press releases, training presentations should be attached, in case the respective costs are being claimed under the direct costs. The Contracting Authority may always ask for more specific information (for example copies of supporting documents during verifications. Further details are provided in Tool 8.

tool 8 – financial reporting details

- Convenient tool to follow

Note: All supporting documentation need to be provided

Some tips for reporting:

tool 9 – REPORTING CHECKLIST

- Convenient tool to follow

  - Get feedback on the process and the progress of your project from your external evaluator/critical friend, you may also organise a ‘reflection and development workshop’ or other assessment event involving your project partners/target group representatives to identify:

  - what went well – and why

  - what didn’t go so well or not well at all – and the reasons why

  - what should be done differently – and why

  - what should stay as originally planned – and why?

- Interim Reports are only concerned with a limited part of the timescale of the project, e.g. the first or second year of implementation only. The Final Report should cover the whole project period

- In completing section about Assessment of the implementation of the action activities and its results of the report do not work on completing it in the order of the format, instead:

  - first write about the project Activities carried out in the period covered by the report

  - secondly write about the Outputs

  - thirdly write about the Outcome(s)

  - after that complete updated Log-frame.

- Take sufficient time to prepare report – it will not be done in 1 day;

- If there are problems/issues report on it, do not hide problems and challenges

- Elaborate clearly: a) What has been achieved in activities implementation, b) Are there any delays? c) What needs to be achieved in the upcoming period;

- Elaborate clearly on results achieved using log-frame. It is very important to demonstrate in the final report the status about the indicators;

- Specific attention to be dedicated to financial reports – checks and supporting documentation to be provided accordingly.

- If you have to commission an auditor – start on time.

## Report on indicators

When reporting on indicators, specific template will be provided to beneficiaries. Namely, the contracting authority will discuss with the beneficiaries the indicators included in their application form and eventually agree upon their revision prior to the contract signature. This is meant to improve the quality of the project indicators to capture the outcomes at the level of overall objective, specific objective(s) and results. The table of the indicators related to the project will become part of the contract and beneficiaries will have the obligation to report on the achievement of the agreed indicators on quarterly basis at regular intervals on 31 March, 30 June, 30 September and 31 December. The value of the chosen indicator is prescribed in the Column Target (include reference year). In exceptional cases, the target value might be changed but with a previous consultation with JTS and approval from the CFCU.

The beneficiaries will be required to set a baseline for the indicators that will be tackled through their project, i.e. they shall include date and value for the base line. The baseline is prescribed in the Column Baseline and it remains unchanged during the reporting.

When reporting, the beneficiaries will use the Column Current Value which dates and values within change accordingly to the reporting period (the date within this column shall be 31 March, 30 June, 30 September and 31 December + YEAR). The values presented within this Column present cumulative value through the reporting period.

The JTS Project officer will be responsible for checking the presented indicators and in communication with the beneficiaries he/she will discuss any possible mismatching of the current and presented values within the reporting period. The beneficiaries shall have clear proof of the presented indicators within the reporting period.

Example:

| Thematic priority 2: Protecting the environment, promoting climate change adaptation and mitigation, risk prevention and management | Baseline |  | Current value |  | Target (2024) |
| --- | --- | --- | --- | --- | --- |
| Specific objective 2: The protection of environmental resources in lake and alpine areas is furthered | Date | Value | Date | Value |  |
| Indicators |  |  |  |  |  |
| Output indicators |  |  |  |  |  |
| Number of awareness campaigns on sustainable use of resources and a cleaner environment | 2022 | 2 | 31/12/2022 | 3 | 3 |
| Outcome indicators |  |  |  |  |  |
| Number of cross-border areas with threatened biodiversity protected/benefited from the actions | 2022 | 1 | 31/12/2022 | 2 | 3 |
| Impact indicators |  |  |  |  |  |
| Number of municipalities having solved/agreed waste management issues through inter-municipal (regional) initiatives | 2022 | 5 | 31/12/2022 | 6 | 6 |

Visibility

C H AP T E R

6

Acording to Article 6(1) of GC - unless the European Commission agrees or requests otherwise, the grant beneficiary(ies) shall take all necessary steps to publicise the fact that the European Union has financed or co-financed the action. Such measures shall comply with the “Communicating and raising EU visibility - guidance for external actions” from July 2022.

This important document is available at:

https://international-partnerships.ec.europa.eu/system/files/2022-07/Communicating%20and%20raising%20EU%20visibility%20-%20Guidance%20for%20external%20actions%20-%20July%202022_0.pdf

This document describes the GBs legal obligations and the mandatory elements of the communication and visibility measures. It sets out requirements and guidelines for briefings, written material, press conferences, presentations, invitations, signs, commemorative plaques and all other tools used to highlight EU participation.

The activities regarding visibility at grant project level will be responsibility of the relevant Grant Beneficiary. The grant beneficiary MUST communicate the project and project results to the target groups (relevant audience – For whom your information is intended?) - Within the country where the action is implemented, within EU (if applicable).

The clear writing tips shared here are based on a presentation by the Plain English Campaign. One can find more information and resources on their website: www.plainenglish.co.uk

Sentence length

  - Use an average sentence length of 15 – 20 words (never go longer than 30).

  - Mix sentence length – short sentences can be very effective.

  - Say only one thing per sentence. When in doubt, use a full-stop.

Vocabulary

  - Use everyday words that you would use at home – vocabulary that your grandparents, neighbours, and friends would understand

  - Avoid jargon and acronyms whenever possible! If you cannot, include a glossary at the beginning of your document.

Tone

  - Use a conversational tone rather than an academic or overly formal one.

  - This does not mean you should use slang or dialect – your writing should still be professional and correct – but your tone should engage your reader and not put them to sleep.

  - Use first and second personal pronouns to refer to your organization and reader (we, us, and you).

Structure

  - Put the most important fact at the beginning of your text so that readers can find it easily – don’t bury it in the middle.

  - Use bullet points rather than long paragraphs.

Content

  - Think like a journalist. Make sure you answer the 5Ws: Who? What? When? Where? Why?

  - Use active sentences, not passive ones

Active: The European Commission published the document in January. Passive: The document was published in January by the European Commission.

tool 10 – communication plan template

tool 10 – communication plan template

- Convenient tool to follow

Before you start writing there are a couple of things you should know:

According to Article 6(2) of your GC - Grant Beneficiaries should take visibility activities very seriously and therefore it is recommended to create a “Communication & Visibility Plan” as per template provided as part of these guidelines within their overall project activity plan. Attached to this Guidelines, in Tool 10, you can find the draft template for such plan.

In particular, the GBs shall mention the action and the IPA CBCP –MNE-ALB 2014-2020 (therefore also European Union's) financial contribution in information given to the final recipients of the grant action, in its internal and annual reports, and in any dealings with the media.

LOGO

GBs should also display the IPA CBC Programme logo wherever appropriate.

It is important that all material have reference to the EU funding and the programme and beneficiary/project logos are clearly visible.

  - All promotional materials shall contain EU and programme logos;

  - Beneficiary(ies) should use their normal stationery in letterheads or fax headers sheets, but should add the phrase “Funded by the European Union” as well as the EU flag when communicating on matters related to the action;

  - The graphic identity of the EU must enjoy an equally prominent place and size as that of the beneficiary(ies).

The logo of the IPA CBC Programme Montenegro – Albania 2014-2020 is available at the following link: https://www.cbc-mne-alb.org/documents/programme-logos

The EU logo is available at the following link:

- English version: https://ec.europa.eu/regional_policy/sources/information-sources/logo-download-center/funded_en.zip

- Montenegrin version: https://ec.europa.eu/regional_policy/sources/information-sources/logo-download-center/funded_bs.zip

- Albanian version: https://ec.europa.eu/regional_policy/sources/information-sources/logo-download-center/funded_ks.zip

PRESS RELEASE

Press release is very fast and accurate communication tool. It can be a very useful contribution to the communication activities around a project. As a rule of thumb, a press release should be issued at the start of all actions.

The release should incorporate the EU logo and Programme logo, mention that this project is funded by the EU and mention the amount of EU funding in Euro. If a press conference is planned, the press release should include the name of an EU, OS and CFCU personality who will be present at the press conference, if appropriate.

At the end, the press release should provide the name of at least one person whom the journalist can contact for further information. Where possible, both work and a mobile telephone number should be provided.

The release should be dated at the top and should also indicate when the information may be released. Generally, journalists prefer to be able to use the release immediately; in this case 'For immediate release' should be written at the top of the document. However, it is sometimes appropriate to stop the release until, for example, the publication of financial figures. In this case, a simple expression such as 'Not to be used before 10:00 hrs, 15 October' should be included at the top of the document.

Tips for creating a good press release

  - Choose a clear, short headline in which you clearly state what the reader is going to learn if he/she dives into the article.

  - Identify your audience and choose the right style accordingly (serious or funny, specific or general) If the press release has to be sent to different targets, change your style/angle (and even the content) to make it useful.

  - One catchy tip is to include a question in the opening line to get the reader's interest. For example: „Have you ever wondered how to recycle fiberglass? The project So and So does it for you!”

  - Use correct grammar and proofread for errors and typos before sending out the information.

  - Add powerful high-resolution photographs or drawings that depict your press release.

LEAFLETS, BROCHURES and BOOKLETS

The language used in publications should be simple, clear and void of EU jargon. Please refrain from producing leaflets which are a copy-paste of your Project Terms of Reference.

It is advised to use your own visual identity in your publications, use photos and illustrations to make publications more appealing to readers. Do use the language that your end user prefers – Montenegrin and Albanian. Print materials in English only if necessary.

Leaflets are simple communication tools used for informing the public about the purpose of an EU project, the proceedings and findings. For example, they are usually A4 format; colour printed on both sides and folded in three parts.

Project brochures are among one of the most essential pieces in the communication tools package to be used during the implementation of a project. Project brochures should contain key information with high quality visuals/photographic illustrations, focusing on objectives, achievements, activities and outputs of the project, along with the correctly placed logos. They can be different in size, usually printed in colour.

On the booklets, EU and programme logo should be present on the cover sheet of the booklet. The details defined for the leaflets should be covered also for the booklets.

Before any printing it is necessary to coordinate with responsible person for visibility if the design and text is appropriate. Before investing time and money in printing please consider the cost benefit effect. For smaller scale project the printing costs should not be excessive.

NEWLETTERS

Newsletters have a key importance and they are used for informing the target group about the progress of a project. Newsletters require a mailing capacity together with an appropriate mailing list. Newsletters can be sent to the target group via internet or they can be broadcasted on the web page. Newsletter formats can be various but on the cover sheet it should be clearly stated that your project is funded by the EU.

Newsletters should only be produced for very specific audience. Do refrain from producing heavy files. Instead, focus on success stories and important news. It is recommended to use email with short news stories directing the reader to the website where more information can be found. Save trees, don't print your newsletters!

WEB PAGES

Since the internet entered in all pores of one society, the websites are becoming to be a basic requirement for communication, but separate websites are not always required for all actions since information can simply be made available via the website of the Grant Beneficiary. It is recommended that websites should only be created if the lifespan of the project is 2 years or longer and has a strong communication component. One should always consider the sustainability of a website, and may prefer to integrate it into the website of the project beneficiary institution.

PUBLIC EVENTS (including press conferences)

Organizing a public event may offer excellent opportunities for generating interest in a project’s achievements. Such events can include conferences, workshops, seminars, fairs, and exhibitions. Those attending to these training courses, conferences, seminars, fairs, exhibitions and workshops should be made aware that the EU is funding the event/project.

In order to easily plan any of the events here is the checklist that should be used to facilitate the event planning. The above presented checklist helps organizing the big events but it can easily be adjusted to fit any need.

| Before the event | During the event | After the event |
| --- | --- | --- |
| - Tasks are allocated to all organizers - Invitations and registration - Budgeting - Welcoming participants - Venue, coffee breaks and catering - Agenda (Speakers? Moderator?) - Photographer - Set up script or roadmap of all details of the event - Invitations sent out in time (speakers, media and participants) - Upon registration, participants receive a confirmation email with the final version of the agenda + - practical information - All organizers are briefed to answer frequently asked questions - Speakers (and the moderator) are briefed - All presentations are compiled and checked - Check technical equipment | - A reception desk is available for registration - Registration sheets - Name badges arranged in alphabetical order(if applicable) - Conference packs (if applicable) and promotional materials - Place labels and water are available for speakers - Conference room equipment is checked - Laptops with presentations - Multimedia projectors and screens - Cables and electricity sockets - Microphones, sound system; persons available for handing out microphones - Air conditioning and lights - Enough toilet facilities are available - There are recycle bins in the conference room - All activities comply with the publicity requirements (e.g. EU flag on display) | - Event documents and photos are uploaded to your website - Conclusions made based on feedback forms and debriefing - All costs and fees are taken care of - All media made a copy of the audio visual materials and deliver it to grant beneficiary |

DISPLAY PANELS

Display panels can be used during events for introducing a project or placed at the main entrance of a training centre/Grant Beneficiary and/or its partner(s) project office, etc. The size of panels varies depending on its contents or whether it is to be portable or not. It is usually made of aluminium and is retractable with the printed roll up.

AUDIO-VISUAL PRODUCTS

Depending on the size of the project and project activities the audio-visual material may be appropriate, but can be expensive to produce, so should only be prepared when there is a realistic chance of it being widely watched. Often there are more efficient ways to promote the project, for example by inviting a TV crew to make a story about the success of your project.

Audio-visual material should focus on the human aspect of your project and how the project has benefited citizens.

Interviews, media statements and TV appearances can be an effective way of informing a broad and diverse audience of your project activities and results. The project team, partners and stakeholders can also be spokespeople of the project and are encouraged to talk to the media but they must always clearly state in their interviews or media appearances that the project is funded by the EU, what the main objectives are related to the EU integration process and list concrete benefits for the citizens. You are encouraged to prepare a brief project fact sheet which you can always distribute to journalists, to make sure important information is not omitted.

SOCIAL MEDIA

Social networking, photo and video sharing applications, blogs and represent the power of social media in our time. The main reason why social media has emerged as an efficient communication tool lies on its interactivity. Users are able to generate content as they have become active online members. Now users not only read information but create their own by expressing their views and sharing information with a potentially large audience. The distribution of online information usually helps reach a wider audience, as posts may deepen on many levels and go viral. Information is disseminated on Facebook and Twitter, pictures are displayed on Instagram and Flickr, community groups created on LinkedIn, videos uploaded to Vimeo and YouTube.

Social media channels of the grant beneficiary institutions should be the first channels of communication. In specific cases, if the project has a longer-term awareness raising component, consider creating your own social media platforms.

JTS and CFCU should be consulted before printing or producing any promotional materials. The purpose of this is not a censorship of any kind, neither editing nor proof reading, but only the verification of the EU visibility requirements.

Steps to follow in this regard are:

- Consult visibility guidelines

- Prepare visibility material

- Send visibility material to JTS for consultation and clearance

- Submit cleared visibility materials to CFCU.

- Obtain approval prior to publishing

Here are some tips to be used:

- Programme logo should always be at the top of visibility materials - to be visible to the public and cameras, with clear funding indication "Funded by the European Union".

- Share information on events and news with the JTS, in this way they will promote your project results as well.

- Logos of GBs should not be placed in the same line as the IPA CBC Programme logo, with a clear indication "project implemented by".

- Promotional materials are usually aimed at local audiences so naturally, they should be primarily in local language, or in the language of the target group.

- Whichever communication tools you decide to use, your messages need to be adjusted to your audience.

- Refrain from using highly technical language, jargon and acronyms; stress how your project makes a difference for the people of Montenegro.

- Mind the environment when printing.

- When organising public events coordinate and agree with JTS and CFCU.

- When organising public events invite the CFCU, respective OSs and EU Delegations to take part, when appropriate.

- Use accurate and information.

Judgment of the General Court (Seventh Chamber) of 15 September 2011, CMB Maschinenbau & Handels GmbH and J. Christof GmbH v European Commission, T-407/07, EU:T:2011:477, paragraph 157.

These principles are Best Value for Money, Avoidance of conflict of interest, Being able to justify the choice of tenderer, Using objective criteria in evaluation, Record keeping  and Respecting EU restrictive measures

Or in local languages: “Finansira Evropska unija“ (in Montenegrin) and “Financuar nga Bashkimi Evropian“ (in Albanian).